## Sheet1
Project: INVENTORY CONTROL SYSTEM
Timeline: 28 March - 10 May 2025
Date Range | Task | Description
March 28 - April 12 | Researching Information | Research on inventory management, SQLite database, Python GUI frameworks (PySimpleGUI, Tkinter, Kivy).
2025-04-13 | Initial Commit | Set up database (angel_store.db) and added initial add_book function.
2025-04-13 | Inventory Display & Update | Added inventory display and update functionality to database.
2025-04-13 | Book Search Function | Implemented get_book_by_name to search books by title.
2025-04-13 | Code Cleanup | Final adjustments: cleaned code, tested all functions thoroughly.
2025-04-13 | Bug Fixes | Fixed bugs and improved overall functionality.
April 14 - April 15 | Researching Information | Research on GUI improvements and better practices.
2025-04-16 | PySimpleGUI Cleanup | Removed unused PySimpleGUI files and references from the project.
April 17 - April 28 | Researching Information | Research on UI design principles, colors, and Kivy layouts.
2025-04-29 | Navigation Enhancements | Added home screen navigation and close button for book display popup.
April 30 - May 6 | Researching Information | Explored color themes, screen transitions, and user experience improvements.
2025-05-07 | UI Enhancement | Added color to MainMenu screen and other screens.
2025-05-07 | Added Buttons | Added Search, Delete, Update buttons for book management.
2025-05-07 | Improved Search | Improved the search functionality to search by title or genre.
2025-05-08 | Gradient Background | Implemented gradient background and aesthetic UI improvements.
2025-05-08 | Full styling | Modified button colors, shapes, background blending for a cohesive look.
2025-05-08 | Documentation | Added README.md, setup instructions, user manual, and project documentation.
2025-05-08 | Pushes | Pushed all changes to GitHub repository.
2025-05-10 | Final adds | Added PowerPoint presentation and Gantt chart